## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| ERP System | Neerujah Ledchumanan | January 19 2021 | 2021-04-20 |  | 20% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  | Stella N. |  | 2021-01-25 | 2021-02-02 | 9 | Complete
| Feature 1 | UI prototype | Stella, Neerujah | 3 | 2021-01-28 | 2021-02-01 | 2 | Complete | frontend
| Feature 2 | Create user page | Yas, Vithura | 3 | 2021-01-29 | 2021-02-01 | 2 | Complete | frontend
| Feature 3 | ERPS-6 User access roles | Nurie | 3 | 2021-01-30 | 1/31/21 | 1 | Complete | backend
| Feature 4 | EPRS-5 User authentication and encryption | Nurie | 3 | 2021-01-31 | 2021-02-01 | 2 | Complete | backend
| Sprint 2 | Front-end & Back-end | M. Nurie |  | 2021-02-03 | 2021-02-24 | 21 | Complete
| Feature 5 | ERPS-8 Define products with different parts | Nurie, Carlin, Stella, Yasaman | 10 | 2021-02-15 | 2021-02-22 | 7 | Complete | frontend & backend
| Feature 6 | ERPS-7 Create and edit the material list required | Nurie, Adam, Carlin, Neerujah, Vithura | 13 | 2021-02-09 | 2021-02-18 | 9 | Complete | frontend & backend
| Feature 7 | ERPS-9 Track inventory | Nurie, Ayman, Mark, Neerujah, Vithura | 21 | 2021-02-11 | 2021-02-22 | 11 | In progress | frontend & backend
| Feature 8 | ERPS-14 Manager is notified from process driven work-flow | Nurie | 8 | 2021-02-12 | 2021-02-19 | 7 | Complete | frontend & backend
| Sprint 3 | Front-end & Back-end | M. Nurie & Stella N. |  | 2/24/21 | 3/17/21 | 19 | Complete
| Feature 9 | ERPS-11 Define order for material and bikes | Nurie, Carlin, Stella, Yasaman | 10 | 2/26/21 | 2021-03-05 | 8 | Complete | frontend & backend
| Feature 10 | ERPS-10 Track quality data | Nurie, Ayman, Mark, Vithura, Neerujah | 8 | 2021-06-03 | 3/13/21 | 8 | Not started | frontend & backend
| Feature 11 | ERPS-46 Create company ledger | Adam, Ayman, Stella, Vithura | 10 | 2021-03-06 | 3/15/21 | 10 | Complete | frontend & backend
| Feature 12 | ERPS-15 View transaction logs | Adam, Ayman, Stella, Neerujah, Yasaman | 13 | 2021-03-05 | 3/15/21 | 11 | Complete | frontend & backend
| Feature 7 | ERPS-9 Track Inventory | Nurie, Mark, Ayman | 5 | 2/25/21 | 2021-03-05 | 9 | In progress | backend
| Sprint 4 | Front-end & Back-end | M. Nurie & Stella N. |  | 3/18/21 | 2021-07-04 | 21 | Complete
| Feature 16 | ERPS-47 Link generated report to Cloud storage | Mark, Adam, Neerujah, Stella | 5 | 2021-04-05 | 2021-04-07 | 3 | Complete | frontend & backend
| Feature 15 | ERps-45 Generate reports in MS excel format | Adam, Mark, Stella, Yasaman | 8 | 3/31/21 | 2021-04-04 | 4 | Complete | frontend & backend
| Feature 14 | ERPS-44 Generate reports in PDF format | Nurie, Ayman, Mark, Vithura, Neerujah | 8 | 3/31/21 | 2021-04-04 | 4 | Complete | frontend & backend
| Feature 13 | ERPS-18 Receive data from production machinery | Carlin, Stella | 11 | 3/18/21 | 3/25/21 | 8 | Not started | frontend & backend
| Feature 10 | ERPS-10 Track quality data | Nurie, Ayman, Vithura, Neerujah | 13 | 3/26/21 | 3/30/21 | 5 | In progress | frontend & backend
| Feature 7 | ERPS-9 Track Inventory | Adam, Mark | 5 | 3/26/21 | 3/30/21 | 5 | Complete | backend
| Sprint 5 | Front-end & Back-end | M. Nurie & Stella N. |  | 2021-08-04 | 4/20/21 | 13 | In progress
| Feature 17 | Touch up UI | Mark, Adam, Neerujah, Stella | 5 | 2021-04-08 | 2021-04-12 | 5 | Not started | frontend
| Feature 18 | Improve test coverage | Carlin, Adam | 3 | 2021-08-04 | 2021-04-10 | 3 | Not started | backend